## Winter 2013
WINTER
AL | Photos |  |  |  | GPS Pt # | Data Sheet Complete | Ref Points | Panorama completed (Y/N) | Sim Priority | Notes
| 50 | 28 | LC | Reshoot?
1 | Double vertical | no | Yes - 28 | no | 1 |  | Yes | N | no, but viewpoint is important. | Stitch pan with view of sign and snowmachines; focus on view to E - SE
3 | Yes | No | No | No |  |  | No | Y |  | Is the pan crooked?
4 | Yes | Yes | Yes - 28 | Possibly |  |  | No | Y |  | Some distortion on the left side of photo? Sound crew and equipment is in photo - can we photoshop out or need new photo?
5 | Yes | No | No | No |  |  | No | Y
6 | Yes | Yes | No | No |  |  | No | Y |  | Cut off left third of panoramic
7 | Yes | Yes | No | Possibly |  |  | No | Y |  | Pan either has a gap in it or it is two separate shots - one of the project and one of a "new view" of Denali
8 | Yes | No | Yes - 28 | no | 8 |  | No | Y
9 | Yes | Yes | No | No | 9 |  | Yes | Y |  | Reference points are snags in picture
10 | Yes | No | No | No | 10 |  | No | Y | No, shows existing T-lines | Shows existing view of transmission lines
11 | Yes | No | Yes - 28 | No | 11 |  | No | Y
12 | Yes | Yes | Yes - 28 | No | 12 |  | No | Y |  | Missing top left corner of pan
13 | Yes | No | No | No | 13 |  | No | N
14 |  |  |  |  | 14 |  | No | N |  | Photo taken from air - no pan
15 |  |  |  |  | 15 |  | No | N |  | Photo taken from air - no pan
16 |  |  |  |  | 16 |  | No | N |  | Not analyzing
17 | Yes | Yes | Yes - 28 | No | 17 |  | Yes | Y |  | Stitch another pan using darker photography
18 |  |  |  |  | 18 |  | No | N |  | Not analyzing
19 | Yes | No | No | Yes | 19 |  | No | Y |  | Pan too wide? Shorten? Notice dark vertical lines in sky -- problem with photographs?
20 | Yes | No | No | no | 20 |  | Yes | Y
21 | Double vertical | No | No | no | 21 |  | No | Y |  | crop photo at lone tree at the left side of photo
22 | Yes | No | Yes - 28 | No | 22 |  | Yes | Y |  | Use short pan
23 | Yes | No | No | No | 23 |  | Yes | Y |  | Remove approx 1/3 of right side of pan?
24 | Yes | No | Yes - 28 | No | 24 |  | No | Y
25 | Yes | Yes | Yes - 28 | No | 25 |  | Yes | Y |  | Pan too wide? Try to create pan with darker photo files?
26 | Yes | Yes | No | No | 26 |  | Yes | Y |  | crop photo approx 1/3 from the right (west) end
27 | Yes | Yes | Yes - 28 | No | 27 |  | Yes | Y
28 | Yes | Yes | Yes - 28 | No | 28 |  | Yes | Y
29 |  |  |  |  | 29 |  | No | N |  | Photo taken from air - no pan - Not analyzing
30 |  |  |  |  | 30 |  | No | N |  | Photo taken from air - no pan - Not analyzing
31 |  |  |  |  | 31 |  | No | N |  | Photo taken from air - no pan - Not analyzing

## Spring 2013
Spring
Spring AL ID | AL ID | Photos |  |  | Reshoot? | GPS Pt | Data Sheet Complete | Ref Points | Pan Completed | Notes
|  | 50mm | 28mm | LCP
SP01 | AL28a | Yes | No | Yes-50 |  |  | No |  | N
SP02 | AL28 | Yes | No | No |  |  | No |  | N
SP03 | AL 1 | Yes | No | No | No |  | No |  | Y | Need more data on landscape surround the AL in different direction and matrix is not completed.
SP04 | AL27 | Yes | No | Yes-28 |  |  | No |  | N
SP05 | AL3 | Yes | No | Yes-28 | no |  | No |  | Y | Need more data on landscape north of AL and if Denali Hwy is visible from this location
SP06 | AL 4 | Yes | No | No | No |  | No |  | Y | Is that a trail in the photo? Not included in analysis
SP07 | AL26 | Yes | Yes | No |  |  | No |  | N
SP08 | AL44 | Yes | No | Yes-28 |  |  | No |  | N
SP09 | AL24 | Yes | Yes | No |  |  | No |  | N
SP10 | AL42 | Yes | No | Yes-28 |  |  | No |  | N
SP11 | AL20 | Yes | Yes | No | No |  | No |  | Y
SP12 | AL50 | Yes | No | No |  |  | No |  | N
SP13 | AL9 | Yes | Yes | Yes |  |  | No |  | N
SP14 | AL23 | Yes | Yes | No |  |  | No |  | N
SP15 | AL6 | Yes | No | No |  |  | No |  | N | Make sure it coincides with the sheets from other seasons at the same AL
SP17 | AL40 | Yes | No | No |  |  | No |  | N
SP18 | HLL | Yes | No | Yes-50 |  |  | No |  | N
SP19 | AL22 | Yes | Yes | No | No |  | Yes | Yes | Y
SP20 | AL25 | Yes | No | Yes-28 |  |  | No |  | N
SP21 |  | No | Yes | No |  |  | NO |  | N
SP22 | AL43 | Yes | No | Yes-28 |  |  | No |  | N
SP23 | AL101 | Yes | No | No |  |  | No |  | N
SP24 | AL45 | Yes | No | No |  |  | No |  | N
SP25 | AL11 | Yes | No | No | No |  | Yes |  | Y | Need to confirm visibility of Kesugi Ridge and co-dominance
SP26 | AL41 | Yes | Yes | Yes-28 |  |  | No |  | N
SP27 | AL46 | Yes | No | Yes-50 |  |  | No |  | N
SP28 | AL8 | Yes | No | No |  |  | No |  | N
SP29 | AL12 | Yes | Yes | Yes-28 | No |  | No |  | Y | Cannot find an 8400-1 form from spring for this AL
SP30 | AL7 | Yes | No | Yes |  |  | No |  | N
SP31 | AL15 | Yes | No | Yes-28 | No |  | No |  | Y | Complete data sheet not recorded and no GPS point taken -- are we going to analyze this one as a spring point?
SP32 | AL19 | Yes | No | No | No |  | No |  | Y | Verify if you can see Fog Lakes and if it is the upland Susitna valley
SP33 | AL21 | Yes | No | Yes - 50 | No |  | No |  | Y | Verify if Chulitna Corridor would be above the treeline and if there are co-dominant views
SP34 |  | Yes | No | No |  |  | No |  | N
SP35 | AL39 | Yes | No | Yes-28 |  |  | No |  | N
SP36 | AL 17 (Stephan Lk) | Yes | No | No | No | No | No |  | Y | Determine res elevation relative to the canyon

## Summer 2013
SUMMER
AL ID | Photos |  |  |  | Data Sheet Complete | Ref points | Panorama completed (Y/N) | Notes / Info Needs
| 50 | 28 | LC | Reshoot?
11 | yes | yes | no | no |  |  | yes
14 | yes | yes | no |  |  |  | yes
28 | yes | yes | no |  |  |  | yes
31 | yes | no | no |  |  |  | yes
32 | yes | no | no |  |  |  | yes
35 | yes | no | no |  |  |  | yes
42 | yes | yes | yes-28 |  |  |  | yes
44 | yes | yes | no |  |  |  | yes
77 | yes | yes | no |  |  |  | yes
100 | yes | yes | no |  |  |  | yes
101 | yes | yes | yes-28 |  |  |  | yes
103 | yes | yes | no |  |  |  | yes
104 | yes | yes | yes-28 |  |  |  | yes
105 | yes | yes | yes-28 |  |  |  | yes
106 | yes | yes | no |  |  |  | yes
107 | yes | yes | no |  |  |  | yes
108 | yes | yes | no |  |  |  | yes
109 | yes | no | no |  |  |  | yes
110 | yes | yes | no |  |  |  | yes
111 | yes | yes | no |  |  |  | yes
112 | yes | no | no |  |  |  | yes
113 | yes | yes | yes-28 |  |  |  | yes
114 | yes | no | no |  |  |  | yes
115 | yes | no | no |  |  |  | yes
116 | yes | no | no |  |  |  | yes
117 | yes | no | no |  |  |  | yes
118 | yes | yes | yes-28 |  |  |  | yes
119 | yes | yes | yes-28 |  |  |  | yes
120 | no | yes | yes-28 |  |  |  | yes
121 | yes | yes | no |  |  |  | yes
122 | yes | no | no |  |  |  | yes
123 | yes | yes | no |  |  |  | yes
140 | yes | yes | yes-28 |  |  |  | yes
141 | yes | yes | no |  |  |  | yes
142 | yes | yes | yes-28 |  |  |  | yes
144 | yes | no | no |  |  |  | yes
145 | yes | yes | no |  |  |  | yes
146 | yes | no | no |  |  |  | yes
147 | yes | yes | no |  |  |  | yes
148 | yes | no | no |  |  |  | yes
150 | yes | yes | no |  |  |  | yes
151 | yes | no | no |  |  |  | yes
152 | yes | no | no |  |  |  | no
153 | yes | no | no |  |  |  | no
160 | yes | yes | no |  |  |  | no
161 | yes | yes | no |  |  |  | no
162 | yes | no | no |  |  |  | no
163 | yes | no | no |  |  |  | no
164 | yes | no | no |  |  |  | no
165 | yes | yes | no |  |  |  | no
166 | yes | yes | no |  |  |  | no
167 | yes | yes | no |  |  |  | no
168 | yes | no | no |  |  |  | no
170 | no | no | yes-28 |  |  |  | no
171 | yes | no | no |  |  |  | yes
172 | yes | no | no |  |  |  | no
173 | yes | yes | no |  |  |  | no
174 | yes | no | no |  |  |  | yes
175 | yes | yes | yes |  |  |  | yes
176 | yes | no | no |  |  |  | no
190 | yes | no | yes-28 |  |  |  | no
191 | yes | yes | no |  |  |  | no
192 | no | yes | no |  |  |  | no
193 | yes | no | no |  |  |  | no
194 | yes | no | yes-28 |  |  |  | yes
195 | yes | no | no |  |  |  | no | photos taken from air, may not be possible to stitch
196 | yes | no | no |  |  |  | no | photos taken from air, may not be possible to stitch
197 | yes | no | no |  |  |  | yes