Aesthetics Resources Progress Report – October 11, 2013

This report outlines work completed as part of the Aesthetic Resource Study, including Visual Resources and Soundscape. Fieldwork was successfully completed on BLM, State of Alaska (including Denali State Park), select private lands, and AHTNA lands located on the Denali Highway.  Work was implemented across all 4 seasons, per commitments contained in the FSP.

Visual Resources

Viewshed models of the proposed corridors (Chulitna, Gold Creek and Denali), Dam Site, and reservoir were generated using GIS.  The resulting polygons established the Primary Study Area.  Though subject to change due to project design refinements, viewshed models created in P1 provided the framework for the Primary Study Area.

The visual resources team spent a total of 24 days in the field collecting baseline data across four seasons. During that time, 148 analysis locations (ALs) were assessed.   No safety incidents occurred during the 2013 field season.

| Table 1. Seasonal Visual Field Summary Table |  |  |  |
| --- | --- | --- | --- |
| Season | Trip Dates | Number of Analysis Locations | Total Days Collecting Data in the Field1 |
| Winter 2013 | March 6, 2013 – March 15, 2013 | 24 | 6 |
| Spring 2013 | May 13, 2013 – May 22, 2013 | 34 | 6 |
| Summer 2013 | July 13, 2013 – July 23, 2013 | 65 | 9 |
| Fall 2013 | September 22, 2013 – September 27, 2013 | 25 | 3 |
| TOTAL |  | 148 | 24 |
| Note: 1Actual days collecting data in the field are shorter than trip duration due to inclement weather and travel days. |  |  |  |

At each AL, high quality photographs were obtained in order to create panoramas used to display baseline conditions and develop photosimulations of project features.  GPS data were collected at each location, and landscape character data were recorded. Viewsheds of the different project components have been generated using GIS models that aided in informed selection of ALs to best analyze the project. As of October 11, 2013 the visual resources team has stitched approximately 60% of the panoramas from the raw photographs taken in the field. The panoramas will be used to generate photo simulations for assessing potential impacts to visual resources. The panoramas from the different ALs are currently being analyzed and summarized for existing landscape character, scenic attractiveness, and scenic integrity to establish baseline conditions for assessing potential impacts. Some general statistics were run on the ALs to understand the distribution of the data collected and ensure it is properly distributed throughout the study area in order to best facilitate a well-rounded, complete analysis.

In The distribution of ALs by land ownership is shown in table 2 below.

| Table 2. Visual ALs by Land Ownership1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Season | Total Analysis Locations | ALs By Land Ownership1 |  |  |  |
|  |  | Federal | State | Private | Ahtna, Incorporated |
| Winter | 24 | 7 | 16 | 0 | 1 |
| Spring | 34 | 5 | 26 | 1 | 2 |
| Summer | 65 | 22 | 39 | 0 | 4 |
| Fall | 25 | 12 | 12 | 0 | 1 |
| TOTAL | 148 | 46 | 93 | 1 | 8 |

1All Analysis Locations visited were on lands where access was granted under the following permits: Ahtna, Incorporated Permit 866 Issued May 15, 2013; Ahtna, Incorporated Permit 873 Issued May 21, 2013; Alaska Mental Health Trust Revocable License for Land Use Issued May 17, 2013; BLM Permit Number AA093571 Issued May 21, 2013; State of Alaska Department of Natural Resources Division of Parks and Outdoor Recreation Permit Number LAS 29000 As Amended Issued May 15, 2013; State of Alaska Department of Natural Resources Division of Parks and Outdoor Recreation Permit Number LAS 29122 Issued May 17, 2013; Matanuska Susitna Borough Land Use Permit MSB006727 Issued June 3, 2013.

Although, some ALs are located in places that are within the viewshed of more than one project component, typically one specific project component was the focus of each AL. The distribution of ALs by land ownership is shown in table 3 below.

| Table 3. Visual ALs By Project Component |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Season | Total Analysis Locations | Reservoir | Dam and Camp Facility Area | Denali Corridor | Chulitna Corridor | Gold Creek Corridor |
| Winter | 24 | 3 | 1 | 8 | 4 | 8 |
| Spring | 34 | 7 | 3 | 9 | 7 | 8 |
| Summer | 65 | 18 | 3 | 19 | 12 | 13 |
| Fall | 25 | 8 | 1 | 6 | 7 | 3 |
| TOTAL | 148 | 36 | 8 | 42 | 31 | 32 |

--introp text on avaialibility

Table 4 below shows the distribution of the project components by landscape character type. This provides some insight regarding which landscape character types could be affected, or provided additional access to. This helps the visual team properly focus the impact analysis as well as provide valuable information for the upcoming preparation of the recreation management plan.

| Table 4. Distribution of Project Components by Landscape Character Type in Acres |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Landscape Character Type | Reservoir | Dam and Camp Facility Area | Denali Corridor | Chulitna Corridor | Gold Creek Corridor |
| Chulitna Moist Tundra Uplands | 0 | 0 | 0 | 13554 | 0 |
| Chulitna Mountains | 0 | 0 | 2610 | 0 | 0 |
| Devils Canyon | 0 | 0 | 0 | 0 | 4182 |
| High Ridges East of Susitna River | 0 | 0 | 0 | 0 | 0 |
| Mid Susitna River Valley | 0 | 0 | 0 | 0 | 3826 |
| Northwest River Valley Area | 0 | 0 | 5921 | 0 | 0 |
| Portage Lowlands | 0 | 0 | 0 | 4405 | 0 |
| Susitna Maclaren Wild and Scenic Section | 0 | 0 | 0 | 0 | 0 |
| Susitna River | 16513 | 4729 | 0 | 259 | 0 |
| Susitna River Canyon | 4820 | 0 | 0 | 0 | 0 |
| Susitna River Valley | 0 | 0 | 0 | 101 | 0 |
| Susitna Upland Terrace | 2135 | 1651 | 0 | 0 | 7962 |
| Susitna Uplands | 77 | 0 | 0 | 0 | 0 |
| Talkeetna Mountains | 0 | 0 | 0 | 0 | 0 |
| Talkeetna Uplands | 0 | 0 | 0 | 0 | 2527 |
| Wet Upland Tundra | 0 | 3199 | 17406 | 1369 | 0 |

Soundscape

As of October 11th 2013, the URS noise team has completed four field seasons for the Susitna-Watana Hydroelectric Project.  A total of 35 days of field data collection occurred over the four seasons. During that time data was collected at 100 analysis locations. No safety incidents occurred during the 2013 field season.

| Table 5. Seasonal Sound Field Summary Table |  |  |  |  |
| --- | --- | --- | --- | --- |
| Season | Trip Dates | Number of Analysis Locations |  | Total Days Collecting Data in the Field1 |
|  |  | Long-Term | Short-Term |  |
| Winter 2013 | March 2, 2013 – March 29, 2013 | 6 | 7 | 11 |
| Spring 2013 | May 16, 2013 – June 2, 2013 | 8 | 2 | 8 |
| Summer 2013 | July 9, 2013 – July 23, 2013 | 8 | 28 | 8 |
| Fall 2013 | September 4, 2013 – September 19, 2013 | 9 | 32 | 8 |
| TOTAL |  | 31 | 69 | 35 |
| 1Includes all days in which field data was being collected. Actual days collecting data in the field are shorter than trip duration due to inclement weather and travel days |  |  |  |  |

At each soundscape AL, ambient soundscape levels were measured. Both short-term and long-term soundscape data was collected. Short-term measurements ranged between 10 minutes to several hours while long-term measurements were collected over a minimum of seven (7) days.  In total, approximately 3,750 hours of ambient noise measurements have been recorded in the study area, with a goal of capturing a representative baseline ambient soundscape within the study area during the seasons of winter, spring, summer, and fall in the year 2013. To date, approximately 1/3 of the recorded data has been processed, beginning with the winter survey and moving forward chronologically. This processing involves reviewing the audio recordings and noise level data hour-by-hour to identify and log significant sound sources and their respective durations in each measurement location.