Aesthetics Resources Progress Report – October 11, 2013

This report outlines work completed as part of the Aesthetic Resource Study, including Visual Resources and Soundscape. Fieldwork was successfully completed on BLM, State of Alaska (including Denali State Park), select private lands, and AHTNA lands located on the Denali Highway.  Work was implemented across all 4 seasons, per commitments contained in the FSP.

Visual Resources

- 25 Planning documents were reviewed for Standards and Guidelines pertaining to Aesthetics Resources

- Viewshed models of the proposed corridors (Chulitna, Gold Creek and Denali), Dam Site, and reservoir were generated using GIS.  The resulting polygons established the Primary Study Area.  Though subject to change due to project design refinements, viewshed models created in P1 provided the framework for the Primary Study Area.

- 24 field days completed to collect baseline data across four seasons. During that time, 148 analysis locations (ALs) were assessed (excluding pre-field logistics and travel).   No safety incidents occurred during the 2013 field season.

- At each AL, high quality photographs were obtained in order to create panoramas used to display baseline conditions and develop photosimulations of project features.

- GPS data were collected at each location, and landscape character data were recorded.

- As of October 11, 2013 the visual resources team has stitched approximately 60% of the panoramas from the raw photographs taken in the field.

- Coordination has occurred with geophysical resources, including ice processes, geomorphology, and hydrology.

- Coordination has occurred with social resources, including recreation, subsistence, and cultural resources.

Data collected are distributed as follows:

| Table 1. Seasonal Visual Field Summary Table |  |  |  |
| --- | --- | --- | --- |
| Season | Trip Dates | Number of Analysis Locations | Total Days Collecting Data in the Field1 |
| Winter 2013 | March 6, 2013 – March 15, 2013 | 24 | 6 |
| Spring 2013 | May 13, 2013 – May 22, 2013 | 34 | 6 |
| Summer 2013 | July 13, 2013 – July 23, 2013 | 65 | 9 |
| Fall 2013 | September 22, 2013 – September 27, 2013 | 25 | 3 |
| TOTAL |  | 148 | 24 |
| Note: 1Actual days collecting data in the field are shorter than trip duration due to inclement weather and travel days. |  |  |  |

| Table 2. Visual ALs by Land Ownership1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Season | Total Analysis Locations | ALs By Land Ownership1 |  |  |  |
|  |  | Federal | State | Private | Ahtna, Incorporated |
| Winter | 24 | 7 | 16 | 0 | 1 |
| Spring | 34 | 5 | 26 | 1 | 2 |
| Summer | 65 | 22 | 39 | 0 | 4 |
| Fall | 25 | 12 | 12 | 0 | 1 |
| TOTAL | 148 | 46 | 93 | 1 | 8 |

1All Analysis Locations visited were on lands where access was granted under the following permits: Ahtna, Incorporated Permit 866 Issued May 15, 2013; Ahtna, Incorporated Permit 873 Issued May 21, 2013; Alaska Mental Health Trust Revocable License for Land Use Issued May 17, 2013; BLM Permit Number AA093571 Issued May 21, 2013; State of Alaska Department of Natural Resources Division of Parks and Outdoor Recreation Permit Number LAS 29000 As Amended Issued May 15, 2013; State of Alaska Department of Natural Resources Division of Parks and Outdoor Recreation Permit Number LAS 29122 Issued May 17, 2013; Matanuska Susitna Borough Land Use Permit MSB006727 Issued June 3, 2013.

Although, some ALs are located in places that are within the viewshed of more than one project component, typically one specific project component was the focus of each AL. The distribution of ALs by land ownership is shown in table 3 below.

| Table 3. Visual ALs By Project Component |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Season | Total Analysis Locations | Reservoir | Dam and Camp Facility Area | Denali Corridor | Chulitna Corridor | Gold Creek Corridor |
| Winter | 24 | 3 | 1 | 8 | 4 | 8 |
| Spring | 34 | 7 | 3 | 9 | 7 | 8 |
| Summer | 65 | 18 | 3 | 19 | 12 | 13 |
| Fall | 25 | 8 | 1 | 6 | 7 | 3 |
| TOTAL | 148 | 36 | 8 | 42 | 31 | 32 |

Soundscape

- A total of 35 days of field data collection occurred over the four seasons.

- Data were collected at 100 analysis locations.

- No safety incidents occurred during the 2013 field season.

- At each soundscape AL, ambient soundscape levels were measured for short- and long-term intervals.

- Short-term measurements ranged between 10 minutes to several hours while long-term measurements were collected over a minimum of seven (7) days.

- In total, approximately 3,750 hours of ambient noise measurements have been recorded in the study area,

- To date, approximately 1/3 of the recorded data has been processed, beginning with the winter survey and moving forward chronologically.

| Table 5. Seasonal Sound Field Summary Table |  |  |  |  |
| --- | --- | --- | --- | --- |
| Season | Trip Dates | Number of Analysis Locations |  | Total Days Collecting Data in the Field1 |
|  |  | Long-Term | Short-Term |  |
| Winter 2013 | March 2, 2013 – March 29, 2013 | 6 | 7 | 11 |
| Spring 2013 | May 16, 2013 – June 2, 2013 | 8 | 2 | 8 |
| Summer 2013 | July 9, 2013 – July 23, 2013 | 8 | 28 | 8 |
| Fall 2013 | September 4, 2013 – September 19, 2013 | 9 | 32 | 8 |
| TOTAL |  | 31 | 69 | 35 |
| 1Includes all days in which field data was being collected. Actual days collecting data in the field are shorter than trip duration due to inclement weather and travel days |  |  |  |  |