## Winter2013_Trimble_Table
FIELD IMPLEMENTATION STATUS TABLE
OBJECTID | Field Analysis Location ID | Status | Location Name | Completed in the Field (Yes/No) | Original Location (Yes/No) | Rationale (If answered No in either previous two columns) | Date Visited | Soundscape Location (Y/N) | NOTES
- | 1 | Planned but not visited | Denali National Park Trail | No | - | Only one tower potentially seen from one point along entire trail | - | -
- | 2 | Planned but not visited | Cantwell | No | - | Vegetation obstructs project views - additional points taken along Denali Highway instead. | - | -
- | 3 | Planned but not visited | Cantwell Gas Station | No | - | - | - | -
4 | 4 | Planned and Visited | Nenana River BLM Overlook | Yes | Yes | - | 2013-03-07 | Yes
- | 5 | Planned and Visited | Brushkana Campground | Yes | Yes | Campground located at inferior position compared to highway and project. Additional visual Analysis Location added along Denali Highway in lieu of campground where views are afforded of project area. Soundscape Analysis Location remained in campground since views are not essential, but sound impacts could still occur. | 2013-03-07 | Yes | No visual data was taken, only sound.
32 | 6 | Planned and Visited | Snowmachine Trail | Yes | Yes | - | 2013-03-11 | No
33 | 7 | Planned and Visited | Brushkana Creek | Yes | Yes | - | 2013-03-11 | Yes | Location moved slightly across river looking north instead of south due to timing restrictions. View looking north will provide insight regarding impacts associated with the Denali corridor and access road.
34 | 8 | Planned and Visited | Big Lake / Deadman Lake | Yes | Yes | - | 2013-03-11 | No | Moved location slightly - approximately 1,500 meters southeast to location that provides better view of Big and Deadman Lake. Analysis Location is still within Denali Corridor footprint.
| 9 | Planned but not visited | Denali Highway Westbound | No | - | Added two new Analysis Locations along the Denali Highway closer to the project footprint also looking west, which would provide better information for assessing potential project impacts. | - | - | -
35 | 10 | Planned and Visited | Chulitna Overlook | Yes | Yes | - | 2013-03-11 | No
- | 11 | Planned but not visited | Portage Creek | No | No | Target Analysis Location was on Tyonik VC land and no access was granted for Winter 2013 trip. Alternative Location 32 was used instead which provides similar views and is on BLM land. | - | - | AL 32 (similar viewing experience) used in place of AL 11.
40 | 12 | Planned and Visited | Gold Creek corridor | Yes | Yes | - | 2013-03-11 | No | Actual analysis location approximately 1,000 meters from target location to get more expansive views. No winter trail observed.
63 | 13 | Planned and Visited | Kesugi - South | Yes | Yes | - | 2013-03-12 | No
28 | 14 | Planned and Visited | Railroad - Chulitna | Yes | Yes | - | 2013-03-10 | No | Actual point taken on RR to gain perspective of train passenger.
26 | 15 | Planned and Visited | Powerline North of Susitna River | Yes | Yes | - | 2013-03-09 | Yes
62 | 16 | Planned and Visited | Kesugi - North | Yes | Yes | - | 2013-03-12 | Yes | Actual location 634 meters east of target location.
31 | 17 | Planned and Visited | Indian River SRA | Yes | No | Actual location moved next to river within OHWL to provide views for those using the river to travel and recreate. | 2013-03-10 | Yes
25 | 18 | Planned and Visited | Powerline South of Susitna River | Yes | No | Target location was on top of a ridge that would not be accessed by recreators or anyone other than for transmission line maintenance. Analyis Location moved downslope approximately 1200 meters. | 2013-03-09 | No
59 | 19 | Planned and Visited | Bridge Site (Downstream) | Yes | Yes | - | 2013-03-12 | No | AL 19 split into two - one D/S of the bridge and one U/S. This location represents view downstream of proposed bridge (looking upstream). Photo taken from the air since target location is on CIRI land, and no access was granted for the Winter 2013 trip.
60 | 19 | Planned and Visited | Bridge Site (Upstream) | Yes | Yes | - | 2013-03-12 | No | AL 19 split into two - one D/S of the bridge and one U/S. Location represents view upstream of proposed bridge (looking downstream). Photo taken from the air since target location is on CIRI land, and no access was granted for the Winter 2013 trip.
58 | 20 | Planned and Visited | New Denali View | Yes | Yes | - | 2013-03-12 | No | "New" view of Denali from project corridor
13 | 21 | Planned and Visited | Stephan Lake | Yes | Yes | - | 2013-03-08 | Yes | Point taken at Stephan Lake air strip
57 | 22 | Planned and Visited | Fog Lakes | Yes | Yes | - | 2013-03-12 | No | New view of Fog Lakes from project corridor. Actual Analysis Location taken approximately 2,700 meters to the southwest to be within project corridor.
27 | 23 | Planned and Visited | South Mountain | Yes | Yes | - | 2013-03-09 | No | -
49 | 24 | Planned and Visited | Watana Creek | Yes | Yes | - | 2013-03-12 | No | View of indundation zone of Watana Creek
45 | 25 | Planned and Visited | Vee Canyon | Yes | Yes | - | 2013-03-12 | No | -
20 | 26 | Planned and Visited | Above High Lake Lodge | Yes | Yes | - | 2013-03-08 | Yes | Actual Analysis Location moved 1500 meters northeast of the target Analysis Location to get an unobstructed view from a superior viewing position.
- | 27 | Planned but not visited | Gold Creek access | No | - | Analysis Location on Tyonik land and no access was granted for Winter 2013 trip. Used Alternate Analysis Location 33 which provides similar views and is on State TAed land. | - | - | -
36 | 28 | Planned and Visited | Denali View | Yes | Yes | - | 2013-03-11 | No | -
- | 29 | Planned but not visited |  | No | - | Removed from list before trip due to distance from project area | - | - | -
- | 30 | Planned but not visited |  | No | - | Removed from list before trip due to distance from project area | - | - | -
- | 31 | Planned but not visited |  | No | - | Removed from list before trip due to distance from project area | - | - | -
39 | 32 | Planned and Visited | Portage Creek | Yes | Yes | - | 2013-03-11 | No | New view up Portage Creek drainage from project corridor.
16 | 33 | Planned and Visited | Gold Creek access | Yes | Yes | - | 2013-03-08 | Yes | Views toward proposed dam site and construction and operation yard.
- | 34 | Planned but not visited | Alpine Lodge Trail | No | - | Could not access site due to weather and distance. Better views available from Analysis Location 35, so that location was used instead. | - | - | -
42 | 35 | Planned and Visited | Watana View | Yes | Yes | - | 2013-03-12 | No | View of proposed reservoir
5 | 36 | New Location Identified in Field | Denali Highway | Yes | No | New Analysis Location identified in field due to newly formed understanding of snowmachine use along the Denali Highway and potential affected views near the western end of the highway. | 2013-03-07 | No
12 | 37 | New Location Identified in Field | Denali Highway west | Yes | No | New Analysis Location identified in field due to newly formed understanding of snowmachine use along the Denali Highway and potential affected views near the western end of the highway. | 2013-03-07 | No
54 | 39 | New Location Identified in Field | Island | Yes | No | New Analysis Location identified in field to document existing landscape character within the Susitna River corridor at an existing island that would be within the proposed inundation zone and no longer exist if the project were implemented. | 2013-03-12 | No
56 | 40 | New Location Identified in Field | Dam Site | Yes | No | New Analysis Location identified in the field to document existing landscape character of the Susitna River immediately downstream of the proposed dam site. | 2013-03-12 | -
61 | 41 | New Location Identified in Field | Existing Transmission Line | Yes | No | Views experienced from AL 41 are from the air and directed toward the existing transmission line that the proposed project would connect into. Existing views experienced from AL 41 provide insight into how the proposed transmission corridors would appear from the air. | 2013-03-12 | - | view from air